## Review Info
Peer Review | Metadata | Reviewer Name | Review Time (Hours)
*Work Product Name: | Peer Review #1 | Deni Cabaravdic | 5
*Work Product Size: |  | Erik Vardumyan | 4.5
Review Start Date: | 2023-03-18 | Kennedy Johnson | 0.8
Review Due Date: | 2023-03-19 | Aaron Gian Madrid | 5
Defect Disposition Meeting Date: | 2023-03-17 | Matthew Kim | 5
Review Completion Date: | 2023-03-19 | Andres Macias | 5
|  | Total (Hrs) | 25.3
Direct Link

## Review Log
Item# | Reviewer Name | Code Module (Code File Name) | Line number | Defect Description or Comment | Major or Minor | Disposition of Defect /Comment | Person Assigned to Resolve | Notes
1 | Kennedy Johnson | Login.js | N/A | Straightforward comments, improvement from previous comments | N/A |  | Front-End Team | Front End Team will be adding another page for the user profile. Was spoken about during a meeting
2 | Kennedy Johnson | SignUp.js | N/A | See above | N/A |  | Front-End Team
3 | Kennedy Johnson | Database.js | N/A | See Above | N/A |  | Front-End Team
4 | Kennedy Johnson | Login.js | N/A | Seems to work fine, more detail could be added to the CSS file | N/A |  | Front-End Team | Front End Team will be adding another page for the user profile. Was spoken about during a meeting
5 | Kennedy Johnson | SignUp.js | N/A | See Above | N/A |  | Front-End Team
6 | Kennedy Johnson | app.py | N/A |  | Minor |  | Deni Cabaravdic
7 | Kennedy Johnson | classificationV2.ipynb | N/A | Could have more descriptive comments throughout the project | Minor |  | Deni Cabaravdic
8 | Kennedy Johnson | simpleColor.py | N/A |  | Major |  | Deni Cabaravdic | No longer a useful component. Will be changing the color model to work with the API
9 | Kennedy Johnson | Login.js | N/A | Improvement on CSS of the login and sign-up pages | Major |  | Front-End Team | Noted in meeting that the entire front end team needs to create another page for the users profile once they are logged in
10 | Kennedy Johnson | SignUp.js | N/A |  | Major |  | Front-End Team
11 | Kennedy Johnson | Login.js | N/A | Straightforward comments, improvements from previous code | Minor |  | Front-End Team/Erik | Recently added on the team, hoping to help with fixing the pages and necessary new ones
12 | Kennedy Johnson | SignUp.js | N/A |  | Minor |  | Front-End Team/Erik
13 | Kennedy Johnson | Login.js | N/A | Improvement on CSS of the login and sign-up pages | Major |  | Front-End Team | Noted in meeting that the entire front end team needs to create another page for the users profile once they are logged in
14 | Kennedy Johnson | SignUp.js | N/A |  | Major |  | Front-End Team
15 | Matthew Kim | database.js | 2023-12-22 | No code issue. | Minor | Understood/Accepted | Aaron | Helped Aaron fix a bug
16 | Matthew Kim | SignUp.js | 2023-01-05 | No code issue. | Minor | Understood/Accepted | Aaron | N/A
17 | Matthew Kim | Login.js | N/A | Establish login reroute to a user dashboard | Major | Understood/ Accepted | Andres | Currently the Login Page is working successfully in terms of authentication, lets go ahead and route the page after login to a user dashboard
18 | Matthew Kim | ImageRecModel/app.py | 0-70 | No code issue | Minor | Understood | Deni | N/A
19 | Matthew Kim | database.js | 2023-12-22 | No code issue. | Minor | Understood/Accepted | Erik | N/A
20 | Matthew Kim | SignUp.js | 2023-01-05 | No code issue. | Minor | Understood/Accepted | Erik | N/A
21 | Matthew Kim | Login.js | 2023-01-05 | No code issue. | Minor | Understood/ Accepted | Erik | N/A
22 | Matthew Kim | colors.py | 50-74 | No code issue | Minor | Understood / Accepted | Kennedy | Kennedy will continue working on the color model to help with the decision making process of our AI
23 | Matthew Kim | ImageRecModel/app.py | 90-101 | No code issue | Minor | Understood | Kennedy | N/A
24 | Erik Vardumyan | Login.js | N/A | After succesful login route to user dashboard | Major | Accepted | Erik and Aaron | Now that Login page is working properly next step is after authentication it is routed to user dashboard
25 | Erik Vardumyan | Database.js | Line 88-91 | No longer need to output username when successful | Minor | Accepted | Erik and Aaron | Now that we have confirmed that it correctly calls from the database and outputs the username we no longer need to output said username. However we can still keep invalid username or password.
26 | Erik Vardumyan | Login.js | N/A | Revamp the login page | Minor | accepted | Andres and FE team | Since it is working successfully, Andres and FE team can start to revamp and make the page more sleak and proffesional. Currently is the skeleton for testing.
27 | Erik Vardumyan | Sign up.js | N/A | Revamp the sign up page | Minor | accepted | Andres and FE team | Since it is working successfully, Andres and FE team can start to revamp and make the page more sleak and proffesional. Currently is the skeleton for testing.
28 | Erik Vardumyan | ImageRecModel app.py | n/a | Continue for accurate results | Major | Accepted | Deni | As mentioned and from the demestration shown. The model is fairly accurate however there are times where it gets the item incorrect. 98% is impressiv. If possible to increase the percentage.
29 | Erik Vardumyan | simpleColor.py | N/A | Improve on the color rec to identify not just the dominent color in the center but to detect top1- 3 main colors of the entire clothing. | Major | Understood | Kennedy or I | Create a more complex version of what we have to not only detect the 200x200 center main color but what other colors are on the clothing to be more accurate for the model
30 | Erik Vardumyan | Login.js | N/A | Revamp the login page | Minor | accepted | Matthew and FE team | Since it is working successfully, Andres and FE team can start to revamp and make the page more sleak and proffesional. Currently is the skeleton for testing.
31 | Erik Vardumyan | Sign up.js | N/A | Revamp the sign up page | Minor | accepted | Matthew and FE team | Since it is working successfully, Andres and FE team can start to revamp and make the page more sleak and proffesional. Currently is the skeleton for testing.
32 | Deni Cabaravdic | SignUp.js | N/A | No code issue | Minor | Understood/ Accepted | Matthew | We need to get some more informative way of registering for a user
33 | Deni Cabaravdic | SignUp.css | N/A | Design Update | Minor | Understood/ Accepted | Matthew | Need to update some updates on this page
34 | Deni Cabaravdic | login.js | N/A | login connection messages | Minor | Understood/ Accepted | Matthew | Establish more informative login messages between the user and their login
35 | Deni Cabaravdic | Imageupload.css | N/A | Design Update | Minor | Understood/ Accepted | Matthew | Need help designing our image upload page
36 | Deni Cabaravdic | Imageupload.js | N/A | Need help with handle submit | Major | Understood/ Accepted | Matthew | difficult to handle submitting between react and the model so we
37 | Deni Cabaravdic | simpleColor.py | N/A | Need to make color scanning detect and output more basic colors | Major | Understood/ Accepted | Kennedy | N/A
38 | Deni Cabaravdic | colors.csv | N/A | Lower the output of colors in this | Major | Understood/ Accepted | Kennedy | This should help give less choice
39 | Deni Cabaravdic | app.py | 35-37 | No code issue | Minor | Understood/ Accepted | Kennedy and Deni | discovered routing between machine learning and react with this
40 | Deni Cabaravdic | app.py | 47-50 | No code issue | Minor | Understood/ Accepted | Kennedy and Deni | Fixed a bug in the flask api
41 | Deni Cabaravdic | classificationV2.ipynb | N/A | No code issue | Major | Understood/ Accepted | Kennedy and Deni | Created more efficient image detecting capabilities
42 | Deni Cabaravdic | database.js, Login.js, Signup.js | N/A | Need to move npm installs into main src folder | Minor | Understood/ Accepted | Erik | Talking with Aaron allows me to see that npm installs need to be moved to the main source folder so that we don't have more thatn one packag.json file within the project and if someone else needs to copy the repo, they can just npm install on the main folder
43 | Deni Cabaravdic | Login.js | N/A | Establish login reroute to a user dashboard | Major | Understood/ Accepted | Erik | We have to route the login to the dashboard on success
44 | Deni Cabaravdic | simpleColor.py | N/A | Make the program accept basic colors so we have a much easier time using a fashion trend api or something similar | Major | Understood/ Accepted | Kennedy or Erik | The colors of an image can be deteced but they are very specific which can cuase some problems due to the amount of colors that exsist. I would say that we can make it work with a limited sortment of colors in order to make sorting clothes out much easier.
45 | Deni Cabaravdic | navbar.js | N/A | Create a better way to getting to image upload | Minor | Understood/ Accepted | Andres | N/A
46 | Deni Cabaravdic | SignUp.css | N/A | Design update | Minor | Understood/ Accepted | Andres | Same thing as login, we have to make it a little more intuitive for the user
47 | Deni Cabaravdic | login.js | N/A | Establish login reroute to dashboard | Major | Understood/ Accepted | Andres | Need to estabish the login page connection to the dashboard in order to get a successful login to the dashboard
48 | Deni Cabaravdic | login.css | N/A | Design update | Minor | Understood/ Accepted | Andres | Need to create a better looking UI for the user when they are using the login
49 | Deni Cabaravdic | navbar.js | N/A | Design Update | Minor | Understood/ Accepted | Andres | Some design features need updating
50 | Deni Cabaravdic | database.js | 37-43 | No code issue | Minor | Understood/ Accepted | Aaron | Helped figure out connection between the database and the code base
51 | Deni Cabaravdic | SignUp.js | 2023-01-05 | No code issue | Minor | Understood/ Accepted | Aaron | N/A
52 | Deni Cabaravdic | login.js | N/A | Fix some of the output messages of the login page when logging in to the datbase | Minor | Understood/ Accepted | Aaron | N/A
53 | Deni Cabaravdic | login.js | 25-34 | No code issue | Minor | Understood/ Accepted | Aaron | Fixed a bug in the register variable
54 | Deni Cabaravdic | database.js | 16-20 | Figured out localhost and how it works with our database | Minor | Understood/ Accepted | Aaron | N/A
55 | Andres Macias | Database.js | 46-51 | Get request should be able to catch and log errors/indicate to user that an error occured | Minor | Issue understood and accepted | Aaron | N/A
56 | Andres Macias | Database.js | 29 | URLs for requests will have to be changed in the future once we host the actual project | Minor | Issue understood and accepted | Aaron | Not an immediate issue, but more or less something to keep in mind.
57 | Andres Macias | app.py | 64-83 | If else list statements can be optimized by instead using pattern matching in python. | Minor | Concern understood | Deni | Would improve readability within the code.
58 | Andres Macias | Signup.js | 13-17 | There are alternative methods that can be used in order to opitmize space rather than utilizing these 5 use state variables. | Minor | Issue understood. | Erik | The code could optimize our space and improve readability.
59 | Andres Macias | Signup.js | 34 | Logging of the response can be removed if testing is complete. Otherwise unnecessary . | Minor | Issue understood and accepted | Erik
60 | Andres Macias | SimpleColor.py | 16 | Lack of variables creates a verbose and confusing code. | Minor | Understood | Kennedy | Creation of variables with proper names can improve readability.
61 | Andres Macias | SimpleColor.py | 1-44 | Proper color predictions as the output that are general are needed to make proper color reccomendations | Major or Minor | Understood/Accepted | Kennedy | Still trying to be completely understood and planned out so that our output of the color model can be properly utilized.
62 | Andres Macias | Signup.js | 2023-12-17 | All of these use state variables are not necessary and can be optimized through alternative methods | Minor | Understood/Accepted | Matthew | Login.js shares the same issue; can improve space complexity and readability.
63 | Andres Macias | Forum.js | N/A | Forum.js needs to be fleshed out further in order for the rest of the team to continue progress with work that involves it. | Major | Understood/Accepted | Matthew & Andres | In progress.
64 | Aaron Gian Madrid | Login.js | N/A | Establish login reroute to a user dashboard | Major | Understood/ Accepted | Erik and FE Team | Currently the Login Page is working successfully in terms of authentication, lets go ahead and route the page after login to a user dashboard
65 | Aaron Gian Madrid | SignUp.js | N/A | Revamp the sign up page | Minor | Aaron Gian Madrid | Andres and FE team | Since it is working successfully, Andres and FE team can start to revamp and make the page more aesthetic and possibly see if any other features can be added to it
66 | Aaron Gian Madrid | Login.js | N/A | Revamp the Login page | Minor | Aaron Gian Madrid | Andres and FE team | Since it is working successfully, Andres and FE team can start to revamp and make the page more aesthetic and possibly see if any other features can be added to it
67 | Aaron Gian Madrid | Navbar.js | N/A | Add Search Bar | Major | Aaron Gian Madrid | Andres and FE team | Establish a navbar search bar to allow me to connect to DB and search up other user profiles.
68 | Aaron Gian Madrid | FashionAPI Connection | N/A | Establish the 2 models to work with Fashion API | Major | Understood/ Accepted | Kennedy and Deni | Now that the two models are working and connected with flask, lets go ahead and see how we'd connect them both to the fashion API for suggestions
69 | Aaron Gian Madrid | ImageRecModel app.py | N/A | Improve Accuracy | Major | Accepted | Deni | The model is functioning better than before and is connected with Flask. Let's work on getting the results more accurate.
70 | Aaron Gian Madrid | database.js | 2023-01-12 | No code issue. Need to move npm installs into main src folder | Minor | Understood/ Accepted | Erik | Let's go ahead and move ourt npm installs to the main source folder so that we don't have more thatn one packag.json file within the project
71 | Aaron Gian Madrid | Login.js | 2023-01-05 | No code issue. Need to move npm installs into main src folder | Minor | Understood/ Accepted | Erik | Let's go ahead and move ourt npm installs to the main source folder so that we don't have more thatn one packag.json file within the project
72 | Aaron Gian Madrid | SignUp.js | 2023-01-05 | No code issue. Need to move npm installs into main src folder | Minor | Understood/ Accepted | Erik | Let's go ahead and move ourt npm installs to the main source folder so that we don't have more thatn one packag.json file within the project
73 | Aaron Gian Madrid | Login.js | N/A | Establish login reroute to a user dashboard | Major | Understood/ Accepted | Erik and FE Team | Currently the Login Page is working successfully in terms of authentication, lets go ahead and route the page after login to a user dashboard
74 | Aaron Gian Madrid | simpleColor.py OR whichever file from ColorRecModel folder | N/A | Determine how the program will identify which colors to detect | Minor | Understood/ Accepted | Kennedy or Erik | I believe the colors are getting identified but lets see if we can get it to where it will select the main colors or a specific dominant color.
75 | Aaron Gian Madrid | simpleColor.py OR whichever file from ColorRecModel folder | N/A | Determine how the program will identify which colors to detect | Minor | Understood/ Accepted | Kennedy or Erik | I believe the colors are getting identified but lets see if we can get it to where it will select the main colors or a specific dominant color.
76 | Aaron Gian Madrid | FashionAPI Connection | N/A | Establish the 2 models to work with Fashion API | Major | Understood/ Accepted | Kennedy and Deni | Now that the two models are working and connected with flask, lets go ahead and see how we'd connect them both to the fashion API for suggestions
77 | Aaron Gian Madrid | Login.js | N/A | Establish login reroute to a user dashboard | Major | Understood/ Accepted | Erik and FE Team | Currently the Login Page is working successfully in terms of authentication, lets go ahead and route the page after login to a user dashboard
78 | Aaron Gian Madrid | SignUp.js | N/A | Revamp the sign up page | Minor | Aaron Gian Madrid | Matthew and FE team | Since it is working successfully, Matthew and FE team can start to revamp and make the page more aesthetic and possibly see if any other features can be added to it
79 | Aaron Gian Madrid | Login.js | N/A | Revamp the Login page | Minor | Aaron Gian Madrid | Matthew and FE team | Since it is working successfully, Matthew and FE team can start to revamp and make the page more aesthetic and possibly see if any other features can be added to it
80 | Aaron Gian Madrid | Forum.js | NA | Format the Forum Page to allow to display users in grid view or list view | Major | Aaron Gian Madrid | Matthew and FE team | Forum page skeletal needs to be established and possibly format the page to have grids for Erik and I to call on DB and display users